## Instructions
INSTRUCTIONS TO FILL OUT THE FORM
S.No | Description
1 | Please follow the instructions given for each item before filling the form
2 | Complete all required fields. Provide the justification, if you leave the space empty
3 | The instructional notes and information fields given, should not be deleted
4 | Add additional row or column as per requirement
5 | Provide the financial status by completing the "Financial Status Sheet"

## EDF Form-III
EXPORT DEVELOPMENT FUND
MINISTRY OF COMMERCE & TEXTILE
(COMMERCE DIVISION)
s
PROJECT COMPLETION FORM - (EDF FORM-III)
To be submitted to the EDF Secretariat at the completion of the project
Pak-Tajikistan Business Forum and Joint Business Council Meeting - Dushanbe Sep 15-16, 2021
2. PROJECT TIME |  |  |  |  | 3. PROJECT COST
Implementation Period |  | Start Date | End Date | Total Project Duration (Years)
Origional as Per EDF Form -I |  | 15th SEP | 16th SEP | 02 days | 32,000 USD + 6,00,000 PKR = 58,80,000 PKR
Actual |  | 14th SEP | 18th SEP | 04 days | 32,606 USD Foreign expenditure + 297,527 PKR local expenditure = 58,73,153 PKR (PKR 302,473 PKR remitted to TDAP HQ)
4. PROJECT OBJECTIVES AND PERFORMANCE INDICATORS
S.No | Project Objective |  | Performance Indicators | Result Against the Performance Indicators
1 | Meeting of Joint Business Council |  | volume of bilateral trade/MOUs/JVs | Agreement on Cooperation signed between FPCCI and Tajik Chamber
2 | To establish linkages with government, business communities and BSOs |  | B2B Meetings | 823 B2B meetings
3 | To increase trade & investemnt in particular with Tajikistan and in general with CARS |  | volume of bilateral trade/MOUs/JVs | 16 MOUs signed/6 contracts signed and more in process
4 | To highlight transit trade potential of Pakistan as gateway to CARs |  | volume of transit trade | Discussions underway regarding enhanced transit trade through CARs
5 | Soft promotion of Pakistan as a Gateway to Cental Asia |  | No. of buyers/traget audience/media | 116 Tajik companies attended the B2B session
5. LIST OF ACTIVITIES
S.No | Activities |  | Start Date | End Date | % of Completion
1 | Visit to Tajik Industrial Units |  | 15th Sep | 15th Sep | 100%
2 | Joint Business Council |  | 16th Sep | 16th Sep | 100%
3 | B2B Meetings |  | 16th Sep | 16th Sep | 100%
4 | Pak-Tajik Business Forum |  | 16th Sep | 16th Sep | 100%
5 | Follow up of B2B Meetings |  | 17th Sep | 17th Sep | 100%
6 | Visit to Tajik Ministry of Industries |  | 17th Sep | 17th Sep | 100%
+
6. LIST OF PROJECT MILESTONES
S.No | Milestones (as per proposal) |  | Time Deadlines |  | Acutal Progress (Achieved/Not Achieved) " if not achieved provide reason of delay"
|  |  | Start latest by | Completed by
1 | Pre-Event Meeting virtual meeting of Pak and Tajik chambers to finalize the agenda of JBC |  | 23rd August | 27th August | Completed
2 | Joint Business Council |  | 16th Sep | 16th Sep | Completed
3 | B2B Meetings |  | 16th Sep | 17th Sep | Completed
4
5
6
7
+
7. PROJECT OUTCOME
Total no. of exporters benefited from the project |  |  |  | 67
% increase in value of exports from the project |  |  |  | To be calculated once MOUs and contaracts materialized
Market diversification |  |  |  | To Tajiikistan specifically and also to other CARs
Product diversification |  |  |  | Textile ,logistics,pharmaceuticals,food,and Especially in Mining sector
Value Addition |  |  |  | Potential exists in food processing sector and joint ventures in mining sector
8. RISK REGISTER
S.No | Risk Description |  |  | Impact (Low/Med/High) | Response Strategy (How to tackled the risk?)
1 | Covid-19 impact |  |  | Medium | SOPs and protocols were strictly followed
2
+
9. TOTAL INCOME FROM SERVICES/REVENUE GENERATION
S.No | Type of Services | Estimated as per EDF Form-I (PKR) |  | Actutal (PKR)
1 | Increase in Trade volume | To be estimated after impact analysis |  | To be estimated after impact analysis
2 | Increase in investment | To be estimated after impact analysis |  | To be estimated after impact analysis
Total Cost of the Project
10.TOTAL FUNDS RECEIVED
S.No | Fund Source |  | FEC* | PKR | Total (PKR)
1 | EDF (as per EDF - Proforma 1) |  | 32000 | 6,00,000 | 32,000 USD + 6,00,000 PKR= 58,80,000/-PKR
2 | EDF (Actual incurred expenditure) |  | 32606 | 297527 | 32606 USD Foreign expenditure + 297,527 PKR local expenditure = 58,73,153 PKR
3 | Other Source 2 (If any) |  | N/A | N/A | N/A
4 | Other Source 3 (If any) |  | N/A | N/A | N/A
Total funds recevied
11. INDICATE PROJECT SUSTAINABILITY MECHANISM AFTER FUNDS UTILIZATION
Review meetings between Pakistani and Tajik businessmen shall be held on quarterly basis for atleast 01 year in order to hold a constructive dialogue on trade related issues, trade promotion and investment. Impact of held activity shall be estimated on quarterly basis in terms of indicators especially value of exports orders received and JVs. Said event will not only generate demand and awareness about transit trade potential of Pakistan but aslo lead to successful implementation of G2G negotiations. Same can be repeated next year in another potential Central Asian country depending on the success of event. Moreover, a single country exhibition can be held later as a follow up to this event.
12. LIST OF ASSESTS (MOVABLE /IMMOVABLE)
Sr. No. | Description of Item |  | Units | Total cost (PKR)
1 | N/A
2 | N/A
3 | N/A
4 | N/A
13. FUTURE COURSE OF ACTION
Keeping in view the feedback received and market analysis Joint Ventures in various sectors would prove beneficial for both sides. A single country exhibition is also proposed to showcase Pakistani products in Tajikistan and enhance the export basket for CARs.
14. RECOMMENDATIONS AND FEEDBACK
Pakistani companies shared very encouraging feedback and express satisfaction over te B2B meetings. Both Tajik and Pakistani businessman had fruitful meetings and signed MOUs and contracts.Tajikistan can be a promising market for Joint Ventures and investment. Arranging B2B meetings and matchmaking is vital for generating business and enhancing exports.However,non availibilty of logistics,direct flights to Tajikistan and banking channels are the loopholes which need to be addressed on prioority by the concerned circles on both sides.
14. PROJECT ACCOUNT DETAIL
A | Nature of Account | Type of Account |  | Date of Opening | Lapsable/Non-Lapsable
PLA
Assignment Account
Current Account
Saving Account
Other
| Account Details | Account Title:
B |  | Branch code:
Address:
Account Number:
C | Details of Interest Earned (PKR)
D | Details of Signatories | Name:
Designation:
Status with project:
E | Status of Account | Date:
Balance as per Bank (attached the bank statement)
* Note: In case of exhibition, please furnish the list of participants (exhibitors) and major brand name and contact numbers for monitoring purpose.
* Note: In case of training, please furnish the list of participants with contact details
Submitted By:
Signature
|  | Name & Designation | Mohammad Ishaq Shinwari (Director)
Telephone No.
|  | E-mail Address | ishaq.shinwari@tdap.gov.pk
Offical Stamp

## Project cost Foreign budget
PROJECT FINANCIAL STATUS (Planned vs Actutal Expenses)
(The items below, are given as example)
S.No | Major Object | Minor Object | Detailed Object | Unit | Unit Cost | Quantity | Amount (PKR)
[7 empty] | Approved Budget | Total Expenses | Variance
1 | Camp Office, Unforeseen Exp related to Venue |  | Room booked in Serena for 04 days to cordinate with delegates | Lump Sum |  |  | 3000 | 461.04 | 2538.96
2 | Priniting and Publication |  | (including standees,backdrops,country booklet,directory,badges,direction signs, stationary etc) | Lump Sum |  |  | 7000 | 7496.46 | -496.46
3 | Meals for 200 participants |  | including Running Tea/coffee for 200,tea break for 200,lunch for 200,forum style 06 tables and chairs for business forum | Lump Sum |  |  | 10000 | 13809.28 | -3809.28
4 | Interpreters/Tanslators/GROs |  | including 25 interprters for the B2B meetings and cordination | Lump Sum |  |  | 6000 | 5700 | 300
5 | Transportation Cost |  |  | Lump Sum |  |  | 4000 | 3846.15 | 153.85
6 | Miscellaneous | [5 empty] | 2000 | 1292.3 | 707.7
| Total Cost of the Project | [5 empty] | 32000 USD | 32606 USD | 606 USD

## Project Cost Local budget
PROJECT FINANCIAL STATUS (Planned vs Actutal Expenses)
(The items below, are given as example)
S.No | Major Object | Minor Object | Detailed Object | Unit | Unit Cost | Quantity | Amount (PKR)
[7 empty] | Approved Budget | Total Expenses | Variance
1 | Design of event theme and branding for the event |  | Desiging of logos, badges,proformas, backdrops and theme of event | Lump Sum |  |  | 150000 | 108900 | 41100
2 | Design and development of soft copy of country booklet and directory |  | Designing and development of country booklet and business delegates directory for event
3 | Gift & Souvenirs | [5 empty] | 3,50,000 | 123156 | 226844
4 | Miscellaneous | [5 empty] | 100000 | 65471 | 34529
| Total Cost of the Project | [5 empty] | 600000 | 297527 | 302473

## Expense List (hidden)
Major Object |  |  | Minor Object | Detailed Object
Code | Description | Code | Description | New | Description | Old
[5 empty] | Pay of Officers (A01101 - A01150) | 1100
A01 | Employee Related Expenses | A011 | Pay | A01101 | Basic Pay | 1101
|  |  |  | A01102 | Personal Pay | 1102
|  |  |  | A01103 | Special Pay | 1103
|  |  |  | A01104 | Technical Pay | 1104
|  |  |  | A01105 | Qualification Pay | 1106
|  |  |  | A01106 | Pay of Contract Staff | 1107
|  |  |  | A01107 | Index Pay | 1105
|  |  |  | A01108 | Pay of Shaheed Police Officers | 1108
|  |  |  | A01109 | Command Pay | newly created
|  |  |  | A01150 | Others | 1199
[5 empty] | Pay of Other Staff (A01151 - 99) | 1200
|  |  |  | A01151 | Basic Pay | 1201
|  |  |  | A01152 | Personal Pay | 1202
|  |  |  | A01153 | Special Pay | 1203
|  |  |  | A01154 | Good Conduct Pay | 1204
|  |  |  | A01155 | Qualification Pay | 1206
|  |  |  | A01156 | Pay of Contract Staff | 1207
|  |  |  | A01157 | Index Pay | 1205
|  |  |  | A01158 | Pay of Shaheed Police Officials | 1208
|  |  |  | A01170 | Others | 1299
[5 empty] | Regular Allowances (A01201 - 10) | 2000
|  | A012 | Allowances | A01201 | Senior Post Allowance | 2100
|  |  |  | A01202 | House Rent Allowance | 2200
|  |  |  | A01203 | Conveyance Allowance | 2300
|  |  |  | A01204 | Sumptuary Allowance | 2400
|  |  |  | A01205 | Dearness Allowance | 2500
|  |  |  | A01206 | Local Compensatory Allowance | 2600
|  |  |  | A01207 | Washing Allowance | 2700
|  |  |  | A01208 | Dress Allowance | 2800
|  |  |  | A01209 | Special Additional Allowance | 2936
|  |  |  | A01210 | Risk Allowance | 2939
[5 empty] | Other Regular Allowances (A01211 - 70) | 2900
|  |  |  | A01211 | Hill Allowance | 2901
|  |  |  | A01212 | Telecommunication Allowance | 2902
|  |  |  | A01213 | Expatriation Allowance | 2903
|  |  |  | A01214 | Postal Operation Allowance | 2904
|  |  |  | A01215 | Extra Departmental Employees Allowance | 2905
|  |  |  | A01216 | Qualification Allowance | 2906
|  |  |  | A01217 | Medical Allowance | 2907
|  |  |  | A01218 | Fixed Contingent/Stationary Allowance | 2908
|  |  |  | A01219 | Foreign Allowance | 2909
|  |  |  | A01220 | Language Allowance | 2910
|  |  |  | A01221 | Accreditation Allowance | 2911
|  |  |  | A01222 | Hardship Allowance | 2912
|  |  |  | A01223 | Exchange Compensation Allowance | 2913
|  |  |  | A01224 | Entertainment Allowance | 2914
|  |  |  | A01225 | Instructional Allowance | 2915
|  |  |  | A01226 | Computer Allowance | 2916
|  |  |  | A01227 | Project Allowance | 2917
|  |  |  | A01228 | Orderly Allowance | 2918
|  |  |  | A01229 | Special Compensation Allowance | 2919
|  |  |  | A01230 | Dusting Allowance | 2920
|  |  |  | A01231 | Drinking Water Allowance | 2921
|  |  |  | A01232 | Performance Evaluation Allowance | 2922
|  |  |  | A01233 | Unattractive Area Allowance | 2923
|  |  |  | A01234 | Training Allowance | 2924
|  |  |  | A01235 | Secretariat Allowance | 2925
|  |  |  | A01236 | Deputation Allowance | 2926
|  |  |  | A01237 | Design Allowance | 2927
|  |  |  | A01238 | Charge Allowance | 2928
|  |  |  | A01239 | Special Allowance | 2929
|  |  |  | A01240 | Utility Allowance for Gas | 2930
|  |  |  | A01241 | Utility Allowance for Electricity | 2931
|  |  |  | A01242 | Consolidated Travelling Allowance | 2932
|  |  |  | A01243 | Special Allowance | 2933
|  |  |  | A01244 | Adhoc Relief | 2934
|  |  |  | A01245 | Indexed House Rent Allowance | 2210
|  |  |  | A01246 | Indexed Conveyance Allowance | 2310
|  |  |  | A01247 | NAB Allowance | 2937
|  |  |  | A01248 | Judicial Allowance | 2935
|  |  |  | A01249 | Utility Allowance to Ministers / Ministers of State | 2938
|  |  |  | A01250 | Incentive Allowance | newly created
|  |  |  | A01251 | Mess Allowance | newly created
|  |  |  | A01252 | Non Practising Allowance | newly created
|  |  |  | A01253 | Science Teaching Allowance | newly created
|  |  |  | A01254 | Anaesthesia Allowance | newly created
|  |  |  | A01255 | Hostel Superintendent Allowance | newly created
|  |  |  | A01256 | Special Adhoc Relief Allowance | newly created
|  |  |  | A01257 | RC Allowance | newly created
|  |  |  | A01258 | Prime Minister's Secretariat Allowance | newly created
|  |  |  | A01259 | Fuel Allowance | newly created
|  |  |  | A01260 | Ration Allowance | 2999
|  |  |  | A01261 | Constiblery Allowance | 2999
|  |  |  | A01262 | Special Relief Allowance | 2940
|  |  |  | A01263 | Reserch Allowance | newly created
|  |  |  | A01264 | Technical Allowance | newly created
|  |  |  | A01265 | Cash Handling Allowance | newly created
|  |  |  | A01266 | Disturbance Allowance | newly created
|  |  |  | A01267 | Warden/Boarding Allowance | newly created
|  |  |  | A01268 | Cost of Living Allowance | newly created
|  |  |  | A01269 | Basic Science Allowance | newly created
|  |  |  | A01270 | Others | 02900-02999
|  |  |  | A012aa | Housing Subsidy Allowance to Government Servants | 2211
[5 empty] | Other Regular Allowances (excluding TA) (A01271 - 99) | 3000
|  |  |  | A01271 | Overtime Allowance | 3100
|  |  |  | A01272 | Night Duty Allowance | 3200
|  |  |  | A01273 | Honoraria | 3300
|  |  |  | A01274 | Medical Charges | 3400
|  |  |  | A01275 | Rest and Recreation Allowance | 3500
|  |  |  | A01276 | Outfit Allowance | 3600
|  |  |  | A01277 | Contingent Paid Staff | 3700
|  |  |  | A01278 | Leave Salary | 3800
|  |  |  | A01279 | Extra Duty Allowance | 3901
|  |  |  | A01280 | Out Station Allowance | 3902
|  |  |  | A01281 | Danger Money Allowance | 3903
|  |  |  | A01282 | Session Allowance | newly created
|  |  |  | A01283 | Field Allowance | newly created
|  |  |  | A01284 | Firewood Allowance | newly created
|  |  |  | A01285 | Motor Cycle Maintenance Allowance | newly created
|  |  |  | A01286 | Suspension Allowance | newly created
|  |  |  | A01287 | Land Revenue Collector's Allowance | newly created
|  |  |  | A01288 | Contract Allowance | 2954
|  |  |  | A01289 | Teaching Allowance | 2941
|  |  |  | A01290 | President / Governor's House Allowance | 2955
|  |  |  | A01291 | Special Allowance for Hiring Drivers to the Parliamentary Secretaries/Chairmen Standing Committees | 2942
|  |  |  | A01299 | Others | 03900 03999
A02 | Project Pre-investment Analysis | A021 | Feasibility Studies | A02101 | Feasibility Studies | 21000
|  |  |  | A02102 | Consultant based Feasibility Studies | newly created
|  | A022 | Reaserch, Surveys and Exploratory Operations | A02201 | Research and Surveys | 22000
|  |  |  | A02202 | Exploratory Operation | 23000
|  |  |  | A02203 | Consultant Based Research and Surveys | newly created
|  |  |  | A02204 | Consultant Based Exploratory Operation | newly created
A03 | Operating Expenses | A031 | Fees | A03101 | Bank Fees | newly created
|  |  |  | A03102 | Legal Fees | newly created
|  | A032 | Communication | A03201 | Postage and Telegraph | 52100
|  |  |  | A03202 | Telephone and Trunk Calls | 52200
|  |  |  | A03203 | Telex, Teleprinter and Fax | 52300
|  |  |  | A03204 | Electronic Communication | newly created
|  |  |  | A03205 | Courier and Pilot Service | 52400
|  |  |  | A03270 | Others | 52900
|  | A033 | Utilities | A03301 | Gas | 53100
|  |  |  | A03302 | Water | 53200
|  |  |  | A03303 | Electricity | 53300
|  |  |  | A03304 | Hot and Cold Weather Charges | 53400
|  |  |  | A03370 | Others | 53900
Occupancy Costs (A03401 - A03470)
|  | A034 | Occupancy Costs | A03401 | Charges | newly created
|  |  |  | A03402 | Rent for Office Building | 58100
|  |  |  | A03403 | Rent for Residential Building | 58200
|  |  |  | A03404 | Rent for Other Buildings | 58300
|  |  |  | A03405 | Rent other than on Building | 58400
|  |  |  | A03406 | Royalties | 58500
|  |  |  | A03407 | Rates and Taxes | 58600
|  |  |  | A03408 | Rent of Machine & Equipment | 58901
|  |  |  | A03409 | Insurance | newly created
|  |  |  | A03410 | Security | newly created
|  |  |  | A03470 | Others | 58900
Operating Leases (A03501 - A03570)
|  | A035 | Operating Leases | A03501 | Machinery and Equipment | newly created
|  |  |  | A03502 | Buildings | newly created
|  |  |  | A03503 | Motor Vehicles | newly created
|  |  |  | A03504 | Computers | newly created
|  |  |  | A03506 | Medical Machinary and Technical Equipment | newly created
|  |  |  | A03570 | Others | newly created
Motor Vehicles (A03601 - A03670)
|  | A036 | Motor Vehicles | A03601 | Fuel | newly created
|  |  |  | A03602 | Insurance | newly created
|  |  |  | A03603 | Registration | newly created
|  |  |  | A03670 | Others | newly created
Consultancy & Contractual Work (A03701 - A3770)
|  | A037 | Consultancy and Contractual Work | A03701 | Computer | newly created
|  |  |  | A03702 | Management | newly created
|  |  |  | A03703 | Government Departments | newly created
|  |  |  | A03770 | Others | newly created
[5 empty] | Government Servants (A03801 - 20) | 51000
|  | A038 | Travel & Transportation | A03801 | Training - Domestic | newly created
|  |  |  | A03802 | Training - International | newly created
|  |  |  | A03803 | Other - Domestic | newly created
|  |  |  | A03804 | Other - International | newly created
|  |  |  | A03805 | Travelling Allowance | 51100 & 51101
|  |  |  | A03806 | Transportation of Goods | 51200
|  |  |  | A03807 | P.O.L Charges, Aeroplanes, Helicoptors, Staff Cars, MotorCycles | 51300
|  |  |  | A03808 | Conveyance Charges | 51400
|  |  |  | A03809 | CNG Charges (Government) | newly created
|  |  |  | A03810 | Tour Expenditure State Conveyance and Motor Cars | 51104
|  |  |  | A03820 | Others | 51900
[5 empty] | Other than Government Servants (A03821 - 40) | 51000
A03 | Operating Expenses | A038 | Travel & Transportation | A03821 | Training - Domestic | newly created
|  |  |  | A03822 | Training - International | newly created
|  |  |  | A03823 | Other - Domestic | newly created
|  |  |  | A03824 | Other - International | newly created
|  |  |  | A03825 | Travelling Allowance | 51102
|  |  |  | A03826 | Transportation of Goods | 51200
|  |  |  | A03827 | P.O.L Charges, Aeroplanes, Helicoptors, Staff Cars, Motorcycles | 51300
|  |  |  | A03828 | Conveyance Charges | 51400
|  |  |  | A03829 | CNG Charges (Non Govt) | newly created
|  |  |  | A03840 | Others | 51900
[5 empty] | General (A03901 - A03971) | New Bifurcation
|  | A039 | General | A03901 | Stationery | 54000
|  |  |  | A03902 | Printing and Publication | 55000
|  |  |  | A03903 | Conferences / Seminars / Workshops / Symposia | 95000
|  |  |  | A03904 | Hire of Vehicles | newly created
|  |  |  | A03905 | Newspapers, Periodicals and Books | 56000 & 56100, 56200
|  |  |  | A03906 | Uniforms and Protective Clothing | 57000
|  |  |  | A03907 | Advertising & Publicity | 59500
|  |  |  | A03908 | Discount given | newly created
|  |  |  | A03909 | Tax Refunds | newly created
|  |  |  | A03910 | Commission Paid | newly created
|  |  |  | A03911 | Loss on Exchange | 93000
|  |  |  | A03912 | Expenditure on Pakistani delegations to Foreign Countries | 92000
|  |  |  | A03913 | Contribution & Subscription | 91100 - 91200
|  |  |  | A03914 | Secret Service Expenditure | 94000
|  |  |  | A03915 | Payments to Government Department for Services rendered | 59100
|  |  |  | A03916 | Essay writing and Copyrights | 59200
|  |  |  | A03917 | Law Charges | 59300
|  |  |  | A03918 | Exhibitions, Fairs and other National Celebrations | 59400
|  |  |  | A03919 | Payments to Other for Services rendered | 59600
|  |  |  | A03920 | Relief and Repatriation of Civilian Internees | 59801
|  |  |  | A03921 | Unforeseen Expenditure for Disaster Preparedness & Relief | 59802
|  |  |  | A03922 | Reimbursement of Interest to Bank | 59803
|  |  |  | A03923 | Security of VIPs | 59804
|  |  |  | A03924 | Expenditure on Refugees, Security, Prisoners & Detainees | 59805
|  |  |  | A03925 | Subsistence Allowance to Detainees | 59806
|  |  |  | A03926 | Allied Branch of the Provincial C.I.D | 59807
|  |  |  | A03927 | Purchase of Drugs and Medicines | 59808
|  |  |  | A03928 | Expenditure on Confiscated Goods | newly created
|  |  |  | A03929 | Weight & Measures, Trade Marks and Patent Rights | newly created
|  |  |  | A03930 | Vocational and Manpower Training | newly created
|  |  |  | A03931 | Expenditure on Foreign Experts Assistance received from Abroad | newly created
|  |  |  | A03932 | Demarcation of Pakistan-India Boundary | newly created
|  |  |  | A03933 | Service Charges | newly created
|  |  |  | A03934 | Re-imbursment of T.T. Charges to Banks for Home Remittances | newly created
|  |  |  | A03935 | Depreciation Expense | newly created
|  |  |  | A03936 | Foreign/Inland Training Course Fee | 59977
|  |  |  | A03937 | Refresher / Recurrent Courses of Pilots | 59944
|  |  |  | A03938 | Insurance of Aircrafts and Pilots | 59945
|  |  |  | A03939 | Landing / Parking Charges of Aircrafts | 59946
|  |  |  | A03940 | Unforeseen Expenditure | 59947
|  |  |  | A03941 | Expense against National Fund for Control of Drug Abuse | 96000
|  |  |  | A03942 | Cost of Other Stores | 59800
|  |  |  | A03943 | HIV/AIDS - Training Foreign | 59910
|  |  |  | A03944 | HIV/AIDS - Local Training and Meetings | 59911
|  |  |  | A03945 | HIV/AIDS - Technical Assistance | 59912
|  |  |  | A03946 | HIV/AIDS - Surveillance | 59913
|  |  |  | A03947 | HIV/AIDS - Monitoring , Research & Evalution | 59914
|  |  |  | A03948 | HIV/AIDS - Behaviour Change Communication and Advocacy | 59915
|  |  |  | A03949 | HIV/AIDS - Services for vulnerable Population | 59916
|  |  |  | A03950 | HIV/AIDS - Drugs & Medical Supplies | 59917
|  |  |  | A03951 | HIV/AIDS - Contigencies | 59918
|  |  |  | A03952 | HIV/AIDS - Operational Cost of Old Surveillance Centers | 59919
|  |  |  | A03953 | Investigation Cost | 59978
|  |  |  | A03954 | Ordnance Store | 59828
|  |  |  | A03955 | Other Store - Tear Gas / Computer, Stationary | 59831
|  |  |  | A03956 | Losses to Local Government and Entities due to Abolition of Taxes | newly created
|  |  |  | A03957 | Special Cost incurred in Performance of Government Functionaries | newly created
|  |  |  | A03958 | Special Expediture Incurred in Executives Directives | newly created
|  |  |  | A03959 | Stipend, Incentives, Awards and Allied Expenditure | 59906
|  |  |  | A03960 | Expenditure on Foreign Delegations arriving in Pakistan | newly created
|  |  |  | A03961 | Discount on Judicial Stamps | newly created
|  |  |  | A03962 | Discount on Non Judicial Stamps | newly created
|  |  |  | A03970 | Others | 59810 & 59900
|  |  |  | A03971 | Cost of State Trading Medicines | newly created
[5 empty] | Pension (A04101 - 4170) | 66000
A04 | Employees Retirment Benefits | A041 | Pension | A04101 | Pension - Civil | 66101
|  |  |  | A04102 | Commuted value of pension-Civil | 66201 & 66203
|  |  |  | A04103 | Gratuity - Civil | 66300 & 66301
|  |  |  | A04104 | Other Pension (e.g. Family Pension) | newly created
|  |  |  | A04105 | Gratuities (e.g. Gratuity where Pension is not Mature) | newly created
|  |  |  | A04106 | Reimbursement of Medical Charges to Pensioners | 66400
|  |  |  | A04107 | Pension - Defence | 66102
|  |  |  | A04108 | Commuted Value of Pension - Defence | 66202 & 66204
|  |  |  | A04109 | Gratuity - Defence | 66300 & 66302
|  |  |  | A04110 | Payment of Pension Contribution of Ex-Local Fund Employees | 66901
|  |  |  | A04111 | Travelling Allowance for Retired Government Servants in connection with journey on Medical Grounds | 66401
|  |  |  | A04112 | Grants to Civil - Defence | New
|  |  |  | A04113 | Superannuation and Retirement Allowance | New
|  |  |  | A04114 | Superannuation Encashment on L.P.R | newly created
|  |  |  | A04170 | Others | 66900
[5 empty] | Subsidy (A05101 - A05120) | 62000
A05 | Grants, Subisidies and Writeoffs of Loans/Advances/Others | A051 | Subsidies | A05101 | Wheat | 62000
|  |  |  | A05102 | Food | 62000
|  |  |  | A05103 | Edible Oil | 62000
|  |  |  | A05104 | Fertilizer | 62000
|  |  |  | A05105 | Tubewells | 62000
|  |  |  | A05106 | Cotton | 62000
|  |  |  | A05120 | Others | 62000
[5 empty] | Grants Domestic (A05201 - A05270) | 64000
|  | A052 | Grants Domestic | A05201 | To Federal Government | newly created
|  |  |  | A05202 | To Provincial Government | 64100
|  |  |  | A05203 | To District Government | 64500
|  |  |  | A05204 | To TMAs | 64600
|  |  |  | A05205 | To Financial Institutions | 64300
|  |  |  | A05206 | To Non Financial Institutions | 64400
|  |  |  | A05207 | To Union Administration | newly created
|  |  |  | A05208 | Local Bodies | 64200
|  |  |  | A05209 | Share from Provincial Allocable Amount | 64501
|  |  |  | A05210 | Special Grants from Provincial Retained Amounts | 64502
|  |  |  | A05211 | Federal Funded Projects | 64503
|  |  |  | A05212 | Special Grants from Provincial Allocable Amounts | 64601
|  |  |  | A05213 | Special Grants from Provincial Retained Amounts | 64602
|  |  |  | A05214 | Federal Funded Projects/Schemes | 64603
|  |  |  | A05215 | Grants to Union Adminstration | 64700
|  |  |  | A05270 | To Others | 64900
[5 empty] | Writeoff of Loans and Advances (A05301 - A05320) | 63000
|  | A053 | Writeoff of Loans and Advances | A05301 | Government Servants | 63000
|  |  |  | A05320 | Others | 63000
[5 empty] | Scholarships (A06101 - A06104) | 65000
A06 | Transfers | A061 | Scholarships, Bonuses and Other Awards | A06101 | Merit Scholarships | 65100
|  |  |  | A06102 | Others Scholarships | 65200 & 65500
|  |  |  | A06103 | Cash Awards | 65400
|  |  |  | A06104 | Bonuses | 65300
[5 empty] | Technical Assistance (A06201 - A06270) | 68000
|  | A062 | Technical Assistance | A06201 | Expenditure on Foreign Trainiees in Pakistan | 68100
|  |  |  | A06202 | Contribution to International Agencies | 68200
|  |  |  | A06270 | Others | newly created
[5 empty] | Entertainments & Gifts (A06301 - A06399) | 67000
|  | A063 | Entertainments and Gifts | A06301 | Entertainments & Gifts | 67000
[5 empty] | Other Transfer Payments (A06401 - A06470) | 69000
|  | A064 | Other Transfer Payments | A06401 | To Foreign Governments | newly created
|  |  |  | A06402 | Contributions / Transfers to Reserve Fund | 69100
|  |  |  | A06403 | Renewals & Replacements | 69200
|  |  |  | A06404 | Return to Government Investment | 69300
|  |  |  | A06405 | To Sugar Cess Fund | newly created
|  |  |  | A06470 | Others | 69900
[5 empty] | Permanent Debt (A07101 - 10) | 61000
A07 | Interest Payment | A071 | Interest - Domestic | A07101 | To Federal Government | 61100
|  |  |  | A07102 | To Provincial Governments | 61100
|  |  |  | A07103 | To District Governments | 61100
|  |  |  | A07104 | To TMAs | 61100
|  |  |  | A07105 | To Financial Institutions | 61100
|  |  |  | A07106 | To Non-Financial Institutions | 61100
|  |  |  | A07110 | Others | 61100
[5 empty] | Floating Debt (A07111 - 20) | 61000
|  |  |  | A07111 | To Federal Government | 61300
|  |  |  | A07112 | To Provincial Governments | 61300
|  |  |  | A07113 | To District Governments | 61300
|  |  |  | A07114 | To TMAs | 61300
|  |  |  | A07120 | Others | newly created
[5 empty] | Unfunded Debt (A07121 - 30) | 61000
|  |  |  | A07121 | To Federal Government | 61400
|  |  |  | A07122 | To Provincial Governments | 61400
|  |  |  | A07123 | To District Governments | 61400
|  |  |  | A07124 | To TMAs | 61400
|  |  |  | A07130 | Others | newly created
[5 empty] | Permanent Debt (A07201 - 10) | 61000
|  | A072 | Interest - Foreign | A07201 | To Federal Government | 61200
|  |  |  | A07202 | To Provincial Governments | 61200
|  |  |  | A07203 | To Financial Institutions | 61200
|  |  |  | A07204 | To Non-Financial Institutions | 61200
|  |  |  | A07210 | Others | 61200
[5 empty] | Other Obligations (A07301 - A07399) | 61000
|  | A073 | Others | A07301 | Other Obligations (e.g. Depreciation and other Reserve Funds, Deposits of Income Tax under Section 18A etc) | 61500
|  |  |  | A07302 | Other Payments (e.g. Management of Loans, Interest of Commercial Banks, Loan on Food Account) | 61600
|  |  |  | A07303 | On Loan received by Post Office etc. | 61700
[5 empty] | Advances to Government Servants (A08101 - A08170) | 85000
A08 | Loans and Advances | A081 | Advances to Government Servants | A08101 | House Building Advance | 85100
|  |  |  | A08102 | Motor Car Advance | 85200
|  |  |  | A08103 | Motor Cycle/Scooter Advance | 85300
|  |  |  | A08104 | Cycle Advance | 85400
|  |  |  | A08170 | Others | 85900
[5 empty] | Loans to Provinces (A08201 - A08210) | 81000
|  | A082 | Provinces | A08201 | NWFP | 81103
|  |  |  | A08202 | Punjab | 81101
|  |  |  | A08203 | Sindh | 81102
|  |  |  | A08204 | Balochistan | 81104
|  |  |  | A08205 | Drought Emergency Relief Assistance | Blocked
|  |  |  | A08206 | Federal DERA Unit (see A08701 and 02) | Blocked
[5 empty] | Loans to Districts / TMAs Government (A08301 - A08310) | 82000
|  | A083 | District Govt/TMAs | A08301 | NWFP | 82000
|  |  |  | A08302 | Punjab | 82000
|  |  |  | A08303 | Sindh | 82000
|  |  |  | A08304 | Balochistan | 82000
|  |  |  | A08310 | Others | newly created
[5 empty] | Loans to Financial Institutions (A08401 - A08499) | 83000
|  | A084 | Loans to Financial Institutions | A08401 | Loans to Financial Institutions | 83000
|  |  |  | A08499 | Others | newly created
[5 empty] | Loans to Non Financial Institutions (A08501 - A08599) | 84000
|  | A085 | Loans to Non Financial Instituiions | A08501 | Loans to Non Finantional Institutions | 84000
|  |  |  | A08599 | Others | newly created
[5 empty] | Loans to Private Sector (A08601 - A08670) | 86000
|  | A086 | Loans to Others | A08601 | Private Sector | 86100
|  |  |  | A08670 | Others | 86900
[5 empty] | DERA Loans (A08701 - A08799) | 81000
|  | A087 | Drought Emergency Relief Assistance | A08701 | Federal DERA Unit | 81105
|  |  |  | A08702 | Drought Emergency Relief Assistance (Provincial) | 81100
[5 empty] | Purchase of Building and Structures (A09101 - A09170) | 19000
A09 | Expenditure on Acquiring of Physical Assets | A091 | Purchase of Building | A09101 | Land and Buildings | newly created
|  |  |  | A09102 | Land and Buildings - Residential Buildings | newly created
|  |  |  | A09103 | Land and Buildings - Office Buildings | newly created
|  |  |  | A09104 | Building and Structure - Others | 19000
|  |  |  | A09170 | Others | Blocked
[5 empty] | Computer Equipment (A09201 - A09299) | newly created
|  | A092 | Computer Equipment | A09201 | Hardware | newly created
|  |  |  | A09202 | Software | newly created
|  |  |  | A09203 | I.T. Equipment | newly created
[5 empty] | Commodity Purchases (A09301 - A09370) | 59700
|  | A093 | Commodity Purhases (Cost of State | A09301 | Food (Sugar) | 59703
|  |  |  | A09302 | Fertilizer | 59704
|  |  |  | A09303 | Coal | 59706
|  |  |  | A09304 | Cost of State Trading - Food (Wheat) | 59701
|  |  |  | A09305 | Cost of State Trading - Food (Rice) | 59702
|  |  |  | A09306 | Cost of State Trading - Others
|  |  |  | A09307 | Provincial Judicial Stamps | newly created
|  |  |  | A09370 | Others | 59709
Other Stores and Stocks (A09401 - A09470)
|  | A094 | Other Stores and Stocks | A09401 | Medical Stores | 59705
|  |  |  | A09402 | Newsprint | 59707
|  |  |  | A09403 | Tractors | newly created
|  |  |  | A09404 | Medical and Laboratory Equipment | newly created
|  |  |  | A09405 | Workshop Equipment | newly created
|  |  |  | A09406 | Storage and Carrying Receptacies | newly created
|  |  |  | A09407 | Specific Consumables | newly created
|  |  |  | A09408 | Generic Consumables | newly created
|  |  |  | A09409 | Medical Stocks | newly created
|  |  |  | A09410 | Life Saving Medical Supplies | newly created
|  |  |  | A09411 | General Utility Chemicals | newly created
|  |  |  | A09412 | Specific Utility Chemicals | newly created
|  |  |  | A09413 | Drapery, Fabrics, Clothing and Allied Material | newly created
|  |  |  | A09414 | Insecticides | newly created
|  |  |  | A09470 | Others | newly created
[5 empty] | Purchase of Transport (A09501 - A09599) | 11000
|  | A095 | Purchase of Transport | A09501 | Purchase of Transport | 11000
|  |  |  | A09502 | Diplomatic Cars | 59708
|  |  |  | A09503 | Others | newly created
[5 empty] | Purchase of Plant and Machinery (A09601 - A09699) | 12000
|  | A096 | Purchase of Plant & Machinery | A09601 | Purchase of Plant & Machinery | 12000
|  |  |  | A09602 | Cold Storage Equipment | newly created
[5 empty] | Purchase of Furniture & Fixture (A09701 - A09799) | 13000
|  | A097 | Purchase of Furniture & Fixture | A09701 | Purchase of Furniture & Fixture | 13000
|  |  |  | A09702 | Unkept Furnishings | newly created
[5 empty] | Purchase of Other Assets (A09801 - A09899) | 14000
|  | A098 | Purchase of Other Assets | A09801 | Purchase of Livestock | 14000
|  |  |  | A09802 | Others | Blocked
|  |  |  | A09899 | Others | newly created
[5 empty] | Principal Repayment (A10101 - A10170) | 87000
A10 | Principal Repayments of Loans | A101 | Principal Repayment of Loans - Domestic | A10101 | Domestic Direct | 87100
|  |  |  | A10102 | To Federal Government | 87200
|  |  |  | A10103 | To Provincial Governments | newly created
|  |  |  | A10104 | To District Governments | newly created
|  |  |  | A10105 | To TMAs | newly created
|  |  |  | A10106 | To Financial Institutions | newly created
|  |  |  | A10107 | To Non Financial Institutions | newly created
|  |  |  | A10108 | Federal Investment Bonds | newly created
|  |  |  | A10109 | Foreign Exchange Bearer Certificates | newly created
|  |  |  | A10110 | US Dollar Bearer Certificates | newly created
|  |  |  | A10111 | Foreign Currency Bearer Certificates | newly created
|  |  |  | A10112 | Special US Dollar Bonds | newly created
|  |  |  | A10113 | Pakistan Investment Bonds | newly created
|  |  |  | A10170 | To Others | newly created
[5 empty] | Repayment of Foreign Loans (A10201 - A010270) | 88000
|  | A102 | Principal Repayment of Loans - Foreign | A10201 | Foreign Direct | 88100
|  |  |  | A10202 | To Federal Government | 88200
|  |  |  | A10203 | To Financial Institutions | newly created
|  |  |  | A10204 | To Non-Financial Institutions | newly created
|  |  |  | A10270 | To Others | newly created
Other Repayments (A10301 - A10399)
|  | A103 | Principal Repayment of | A10301 | Other Repayments | 89000
[5 empty] | Repayment of Floating Debts (A10401 - A10499) | newly created
|  | A104 | Principal Repayment of Loans - Floating Debts | A10401 | Prize Bonds | newly created
|  |  |  | A10402 | Treasury Bills | newly created
|  |  |  | A10403 | Ways and Means Advances | newly created
|  |  |  | A10404 | Cash Credit Accommodation | newly created
[5 empty] | Domestic Investment (A11101 - 11170) | 71000
A11 | Investments | A111 | Investment - Domestic | A11101 | To Financial Institutions | 71000
|  |  |  | A11102 | To Non-Financial Institutions | 72000
|  |  |  | A11170 | To Others | newly created
[5 empty] | Foreign Investments (A11201 - A11270) | 73000
|  | A112 | Investment - Foreign | A11201 | To Financial Institutions | newly created
|  |  |  | A11202 | To Non-Financial Institutions | newly created
|  |  |  | A11203 | Contribution to International Financial Institutions | 73000
|  |  |  | A11270 | To Others | newly created
[5 empty] | Other Investments (A11301 - A11399) | 79000
|  | A113 | Investment - Others | A11301 | Others | 79000
[5 empty] | Roads, Highways and Bridges (A12101 - A12199) | 31000
A12 | Civil Works | A121 | Roads, Highways and Bridges | A12101 | Highways | 31100
|  |  |  | A12102 | Other Roads | 31200
|  |  |  | A12103 | Bridges of National Importance | 31300
|  |  |  | A12104 | Other Bridges | 31400
[5 empty] | Irrigation Works (A12201 - A12270) | 32000
|  | A122 | Irrigation Works | A12201 | Main Canals | 32100
|  |  |  | A12202 | Feeder Canals | 32200
|  |  |  | A12203 | Tertiary and Other Subsidiary Links | 32300
|  |  |  | A12204 | Agricultural Produce Carrying Equipment | NEW
|  |  |  | A12270 | Others | 32900
Embankments and Drainage Works (A12301 - 12370)
|  | A123 | Embankments and Drainage Works | A12301 | Main Embankment | 33100
|  |  |  | A12302 | Miscellaneous Embankment | 33200
|  |  |  | A12303 | Drainage | 33300
|  |  |  | A12370 | Others | 33900
[5 empty] | Building and Structure (A12401 - 12470) | 34000
|  | A124 | Building and Structures | A12401 | Office Buildings | 34100
|  |  |  | A12402 | Residential Buildings | 34200
|  |  |  | A12403 | Other Buildings | 34300
|  |  |  | A12404 | Structures | 34400
|  |  |  | A12405 | Electrification Plumbing and Other Infrastructure | newly created
|  |  |  | A12470 | Others-Civil Works Consturction of Building & Structure | 34900 & 34500
Other Works (A12501 - A12599)
|  | A125 | Other Works | A12501 | Works - Urban | newly created
|  |  |  | A12502 | Works - Rural | newly created
[5 empty] | Telecommunication Works (A12601 - A12620) | 35000
|  | A126 | Telecommunic ation Works | A12601 | Lines and Wires | 35100
|  |  |  | A12602 | Apparatus and Plants | 35200
|  |  |  | A12603 | Share in Factories | 35300
|  |  |  | A12604 | Stores | 35400
|  |  |  | A12605 | Construction of Lines and Wires (Telegraph) | 35101
|  |  |  | A12606 | Construction of Lines and Wires (Telephone) | 35102
|  |  |  | A12607 | Construction of Lines and Wires ( Radio ) | 35103
|  |  |  | A12608 | Construction of Apparatus and Plants ( Telegraph ) | 35201
|  |  |  | A12609 | Construction of Apparatus and Plants ( Telephone ) | 35202
|  |  |  | A12610 | Construction of Apparatus and Plants (Radio ) | 35203
|  |  |  | A12620 | Others | 35900
[5 empty] | DERA Works (A12701 - A12799) | 36000
|  | A127 | Drought Emergency Relief Assistance | A12701 | Works | 36100
|  |  |  | A12702 | Goods & Commodities | 36200
|  |  |  | A12703 | Consultant Services &Training | 36300
|  |  |  | A12704 | Incremental Operational Cost (Establishment Charges) | 36400
[5 empty] | Transport (A13001 - A13099) | 41000
A13 | Repairs and Maintenance | A130 | Transport | A13001 | Transport | 41000
[5 empty] | Machinery and Equipment (A13101 - A13199) | 42000
|  | A131 | Machinery and Equipment | A13101 | Machinery and Equipment | 42000
|  |  |  | A13199 | Repair & Maintenance of Others | newly created
[5 empty] | Furniture and Fixture (A13201 - 13299) | 43000
|  | A132 | Furniture and Fixture (R&M) | A13201 | Furniture and Fixture | 43000
[5 empty] | Building and Structure (A13301 - 13370) | 44000
|  | A133 | Buildings and Structure | A13301 | Office Buildings | 44100
|  |  |  | A13302 | Residential Buildings | 44200
|  |  |  | A13303 | Other Buildings | 44300
|  |  |  | A13304 | Structures | 44400
|  |  |  | A13370 | Others - Repair and Maintenance of Building & Structures | 44900 & 44500
[5 empty] | Irrigation (A13401 - A13470) | 45000
|  | A134 | Irrigation | A13401 | Main Canals | 45100
|  |  |  | A13402 | Feeder Canals | 45200
|  |  |  | A13403 | Tertiary and other Subsidiary Links | 45300
|  |  |  | A13470 | Others | 45900
[5 empty] | Embankments and Drainage (A13501 - A13570) | 46000
|  | A135 | Embankment and Drainage | A13501 | Main Embankment | 46100
|  |  |  | A13502 | Miscellaneous Embankment | 46200
|  |  |  | A13503 | Drainage | 46300
|  |  |  | A13570 | Others | 46900
[5 empty] | Roads, Highways and Bridges (A13601 - A13699) | 47000
|  | A136 | Roads, Highways and Bridges | A13601 | Highways | 47100
|  |  |  | A13602 | Other Roads | 47200
|  |  |  | A13603 | Bridges of National Importance | 47300
|  |  |  | A13604 | Other Bridges | 47900
[5 empty] | Computer Equipment (A13701 - A13799) | newly created
|  | A137 | Computer Equipment | A13701 | Hardware | newly created
|  |  |  | A13702 | Software | newly created
|  |  |  | A13703 | I.T. Equipment | newly created
[5 empty] | General (A13801 - A13899) | 49000
|  | A138 | General | A13801 | Maintenance of Gardens | 49100
[5 empty] | Telecommunication Works (A13901 - A13920) | 48000
|  | A139 | Telecommunic ation Works | A13901 | Lines and Wires - Repair | 48100
|  |  |  | A13902 | Apparatus and Plants | 48200
|  |  |  | A13903 | Repair and Maintenance of Lines and Wires (Telegraph) | 48101
|  |  |  | A13904 | Repair and Maintenance of Lines and Wires (Telephone) | 48102
|  |  |  | A13905 | Repair and Maintenance of Lines and Wires ( Radio ) | 48103
|  |  |  | A13906 | Repair and Maintenance of Apparatus & Plants ( Telegraph ) | 48201
|  |  |  | A13907 | Repair and Maintenance of Apparatus & Plants (Telephone ) | 48202
|  |  |  | A13908 | Repair and Maintenance of Apparatus and Plants (Radio ) | 48203
|  |  |  | A13920 | Others - Repair | 48900
Suspense and Clearing (A14101 - A14199)
A14 | Suspence and Cleariing | A141 | Recovery of Expenditure | A14101 | Recovery of Expenditure Suspense | newly created
Taxes from Companies
|  |  |  | A99999 | Default Down Payment Account Dummy | 99999

## Project Output (hidden)
Project Output (Export Acitivity)
01-Export Marketing events
02-Training Infrastructure
03-Compliance Infrastructure
04-Software/Applications/Website
05-Subsidization of Export Services
06-Training Services
07-Export Marketing Infrastructure
08-Legal Services
09-Secretariat
10-Compliance Certifications/Services
11-Research Studies
12-Policy Development
13-Testing and CFCs

## Beneficiaries List (hidden)
Type of Entity
01-Commerce Division
02-Other Government Agencies
03-Associations
04-Chambers
05-Non Profit Organizations
06-Universities/Institutes
07-Commissioning Board
08-Companies/Zones